## Unlicensed version
Unlicensed version. Please register @ templater.info

## Deckblatt
Checkliste / Check list |  |  |  |  | Güdel-Logo
Seite 1 von 2
Customer Projects - Sub Project Manager Job Site Management
v{{DocV}} |  | {{DocumentName}} |  | {{DocumentNo}}
Revision |  | Document Name |  | Document Number
{{DateIssued}} | {{DocumentOwner}} |  | {{DateReleased}} | {{ReleasedBy}}
Issue Date | Issued by |  | Release Date | Released by
The valid version of this document is stored in the Document Management System. All printed copies are for information only.
For reasons of the legibility the male form was chosen in the text. The information refers nevertheless to members of all genders.

## Checklist
Güdel-Logo
Customer Projects - Sub Project Manager Job Site Management | [7 empty] | Seite 2 von 2
Number | Activity | Milestone |  |  | Link Milestone checklist | Milestone / Activity check | Comment
3. | Project Kick-off |  |  |  |  | check
Number |  |  | Inputs | Input from | Link / Workinstruction | Input check (OK ¦ NOK ¦ N/A) | Comment
3.1.1 |  |  | Invitation to Project Kick-off meeting | Project Manager |  | check
3.1.2 |  |  | Project folder | Project Manager |  | check
3.1.3 |  |  | Project opened in SAP | Project Manager |  | check
3.1.4 |  |  | Lesson learned former projects | Former Projects |  | check
Number |  |  | Outputs | Output to | Link / Workinstruction | Output State (Open ¦ Done ¦ Work ¦N/A) | Comment
3.2.1 |  |  | Project Kick-off presentation |  |  | -
3.2.2 |  |  | Create Assembly / Commissioning time schedule | Project Manager | Installation Schedule Press Automation | -
3.2.3 |  |  | Prepare Jobsite Condition & Infrastructure requirements |  | Job Site Condition & Infrastructure Requirement | -
3.2.4 |  |  | Check/prepare travel requirements (Country, Visa etc) |  | Checklist Travel Job Site Access | -
3.2.5 |  |  | Prepare Jobsite initial material list |  | Job Site Initial Material | -
Number | Activity | Milestone |  |  | Link Milestone checklist | Milestone / Activity check | Comment
4. | Customer Kick-Off |  |  |  |  | check
Number |  |  | Inputs | Input from | Link / Workinstruction | Input check (OK ¦ NOK ¦ N/A) | Comment
4.1.1 |  |  | Invitation to Customer project kick-off meeting | Project Manager |  | check
4.1.2 |  |  | Specification / Technical Agreement - draft version | Project Manager |  | check
4.1.3 |  |  | Sales Layout | Mechanical Engineer |  | check
4.1.4 |  |  | Contract | Sales Manager |  | check
4.1.5 |  |  | Project scope | Sales Manager |  | check
4.1.6 |  |  | Time schedule | Project Manager |  | check
4.1.7 |  |  | Budget | Sales Manager |  | check
Number |  |  | Outputs | Output to | Link / Workinstruction | Output State (Open ¦ Done ¦ Work ¦N/A) | Comment
4.2.1 |  |  | Customer Kick-Off Meeting minutes |  |  | - | OneNote
4.2.2 |  |  | Specification / Technical Agreement - reviewed version |  |  | -
4.2.3 |  |  | Time schedule coordinated |  |  | -
4.2.4 |  |  | Scope of Supply matched |  |  | -
4.2.5 |  |  | Sales layout reviewed |  |  | -
4.2.6 |  |  | Milestone with customer fixed (FAT, SOB, Installation, Commissioning, PMA, FAC) |  |  | -
4.2.7 |  |  | Check installation country regulation and site access |  | Entsendungen von GCH ins Ausland | -
4.2.8 |  |  | Update travel/jobsite access requirements |  | Checklist Travel Job Site Access | -
4.2.9 |  |  | Prepare cable installation guideline |  | Cable Installation Guideline | -
Number | Activity | Milestone |  |  | Link Milestone checklist | Milestone / Activity check | Comment
16. | Final Inspection & Internal FAT |  |  |  |  | check
Number |  |  | Inputs | Input from | Link / Workinstruction | Input check (OK ¦ NOK ¦ N/A) | Comment
16.1.1 |  |  | Final Inspection summary | Assembly |  | check
16.1.2 |  |  | Internal FAT summary | Software Engineer |  | check | OneNote
Number |  |  | Outputs | Output to | Link / Workinstruction | Output State (Open ¦ Done ¦ Work ¦N/A) | Comment
16.2.1 |  |  | Test plan and Checklist for customer FAT |  |  | -
16.2.2 |  |  | Invitation for assembly lessons learned meeting |  |  | -
Number | Activity | Milestone |  |  | Link Milestone checklist | Milestone / Activity check | Comment
17. | Customer FAT / Final Inspection |  |  |  |  | check
Number |  |  | Inputs | Input from | Link / Workinstruction | Input check (OK ¦ NOK ¦ N/A) | Comment
17.1.1 |  |  | Invitation for FAT meeting | Project Manager |  | check
17.1.2 |  |  | Draft Version documentation | Documentation |  | check
17.1.3 |  |  | Checklists [Prüffeld] (mechanical, electrical, software, safety) | Assembly / Software Engineer |  | check
17.1.4 |  |  | Support Customer/project manager at FAT if necessary | Engineering |  | check
17.1.5 |  |  | Lesson Learned | Assembly / Engineering |  | check
Number |  |  | Outputs | Output to | Link / Workinstruction | Output State (Open ¦ Done ¦ Work ¦N/A) | Comment
17.2.1 |  |  | Customer FAT meeting minutes |  |  | -
17.2.2 |  |  | FAT document signed |  |  | -
17.2.3 |  |  | Improvements/list of open points documented |  | Project List Open Points | -
17.2.4 |  |  | Prepare/Fill in Jobsite folder with necessary documents |  |  | - | SharePoint
Number | Activity | Milestone |  |  | Link Milestone checklist | Milestone / Activity check | Comment
18. | Shipping Kick-off |  |  |  |  | check
Number |  |  | Inputs | Input from | Link / Workinstruction | Input check (OK ¦ NOK ¦ N/A) | Comment
18.1.1 |  |  | Invitation to Shipping Kick-off meeting | Project Manager |  | check
18.1.2 |  |  | Documentation in source language for final technical review | Documentation |  | check
18.1.3 |  |  | Open points from FAT solved | Project Team |  | check | OneNote
18.1.4 |  |  | Updated safety documentation (if needed) | Safety Engineer |  | check
Number |  |  | Outputs | Output to | Link / Workinstruction | Output State (Open ¦ Done ¦ Work ¦N/A) | Comment
18.2.1 |  |  | Prepare tool list for Carnet Ata | Logistic |  | -
18.2.2 |  |  | Shipping documentation for customer |  |  | -
18.2.3 |  |  | Save documents for external assembly on SharePoint |  |  | - | SharePoint
18.2.4 |  |  | Shipping Kick-Off Meeting minutes |  |  | - | OneNote
Number | Activity | Milestone |  |  | Link Milestone checklist | Milestone / Activity check | Comment
19. | Attending Shipping Control |  |  |  |  | check
Number |  |  | Inputs | Input from | Link / Workinstruction | Input check (OK ¦ NOK ¦ N/A) | Comment
19.1.1 |  |  | Invitation to Shipping Control meeting | Assembly |  | check
19.1.2 |  |  | Pictures of the packaging made | Assembly |  | check
19.1.3 |  |  | Final version of the documentation in all required languages (if required) | Documentation |  | check
19.1.4 |  |  | Export documents | Logistic |  | check
Number |  |  | Outputs | Output to | Link / Workinstruction | Output State (Open ¦ Done ¦ Work ¦N/A) | Comment
19.2.1 |  |  | Completed export list |  |  | -
Number | Activity | Milestone |  |  | Link Milestone checklist | Milestone / Activity check | Comment
20. | Site Kick-off |  |  |  |  | check
Number |  |  | Inputs | Input from | Link / Workinstruction | Input check (OK ¦ NOK ¦ N/A) | Comment
20.1.1 |  |  | Invitation customer for Site Kick-off | Project Manager / Jobsite Manager |  | check
20.1.2 |  |  | Time Schedule - Assembly / Commissioning | Jobsite Manager | Installation Schedule Press Automation | check
20.1.3 |  |  | Jobsite safety assessment documents | Safety Manager |  | check
Number |  |  | Outputs | Output to | Link / Workinstruction | Output State (Open ¦ Done ¦ Work ¦N/A) | Comment
20.2.1 |  |  | Site Kick-off Meeting Minutes | Customer | Meeting Minutes | -
20.2.2 |  |  | Coordinated time schedule - Assembly / Commissioning | Customer |  | -
20.2.3 |  |  | Sign Jobsite Guideline | Project Manager | Gudieline Jobsite Manager | -
20.2.4 |  |  | Add local contacts to Jobsite safety Instruction |  | Job Site Safety Instruction | -
20.2.5 |  |  | Handover cable installation guideline to installation company | Contractor | Cable Installation Guideline | -
20.2.6 |  |  | Safety Instruction training for installations staff and contractor |  | Job Site Safety Training Participation List | -
20.2.7 |  |  | Start Open issue list for jobsite tasks | Project Team | Project List Open Points | -
20.2.8 |  |  | Continuous update of the absence abroad list |  | Day Counter Foreign Countries | -
20.2.9 |  |  | Check reguarly Scope of work |  | Job Site Scope of Work | -
20.2.10 |  |  | Checking the installation and completing the checklist |  | Inspection Test Plan PressAutomation | -
20.2.11 |  |  | Handover of documentation to the customer | Customer | Job Site Documentation handover | -
20.2.12 |  |  | Weekly Jobsite Report | Project Manager | Job Site - Weekly Report | - | Template Job Site Weekly Report
20.2.13 |  |  | Meeting minutes document for issues (if needed) |  | Meeting Minutes | -
20.2.14 |  |  | Maintenance & Operator training |  | Job Site Training Participation List | -
20.2.15 |  |  | Weekly time management for SAP |  | Job Site Recording of working time | - | Projekt-Auftrag-Einsatz-Abrechnung
20.2.16 |  |  | Reporting task for job site manager |  | Reporting tasks for Job Site | -
20.2.17 |  |  | Cost accounting for expense |  | Cost accounting for expense | -
20.2.18 |  |  | Safety Checklist for Commissioning - Trial Operation | Commissioning Engineer | Safety Check Commissioning Trial Operation | - | Job Site manager together with Commisioning manager
20.2.19 |  |  | Instruction for safe work in trial operation | Commissioning Engineer | Safe working on systems in trial operation | - | Job Site manager together with Commisioning manager
Number | Activity | Milestone |  |  | Link Milestone checklist | Milestone / Activity check | Comment
21. | Open Box Inspection |  |  |  |  | check
Number |  |  | Inputs | Input from | Link / Workinstruction | Input check (OK ¦ NOK ¦ N/A) | Comment
21.1.1 |  |  | Invitation customer for Open Box Inspection meeting | Jobsite Manager |  | check
21.1.2 |  |  | Checklist / Export list / Media | Project Manager |  | check
Number |  |  | Outputs | Output to | Link / Workinstruction | Output State (Open ¦ Done ¦ Work ¦N/A) | Comment
22.2.1 |  |  | Open Box Inspection meeting minutes | Customer/Project Manager | Job Site Statement of arrival | -
22.2.2 |  |  | Unloading transport damage information documented | Logistic |  | -
Number | Activity | Milestone |  |  | Link Milestone checklist | Milestone / Activity check | Comment
22. | PMA |  | PMA = Preliminary Acceptance Test |  |  | check
Number |  |  | Inputs | Input from | Link / Workinstruction | Input check (OK ¦ NOK ¦ N/A) | Comment
22.1.1 |  |  | Invitation customer for PMA | Project Manager / Jobsite Manager |  | check
22.1.2 |  |  | Handover of documentation made to the customer | Jobsite Manager |  | check
22.1.3 |  |  | Signed Safety Instruction | Jobsite Manager |  | check
22.1.4 |  |  | Trainings documented | Jobsite Manager |  | check
22.1.5 |  |  | Safety assessment document / open issue list | Safety Engineer |  | check
22.1.6 |  |  | Open issue list agreed | Customer |  | check
Number |  |  | Outputs | Output to | Link / Workinstruction | Output State (Open ¦ Done ¦ Work ¦N/A) | Comment
22.2.1 |  |  | PMA meeting minutes | Customer / Project Manager | Meeting Minutes | -
22.2.2 |  |  | PMA document signed | Customer / Project Manager | PMA Document_EN | - | The benefits and the risks of loss, damage or destruction of the equipment shall pass to the Customer as of the date of completed PMA
22.2.3 |  |  | Open issue list updated | Customer / Project Team |  | -
22.2.4 |  |  | Changes documented from the jobsite | Project Manager |  | -
Number | Activity | Milestone |  |  | Link Milestone checklist | Milestone / Activity check | Comment
23. | FAC |  | FAC = Final Acceptance Certificate |  |  | check
Number |  |  | Inputs | Input from | Link / Workinstruction | Input check (OK ¦ NOK ¦ N/A) | Comment
23.1.1 |  |  | Invitation customer for FAC | Project Manager / Jobsite Manager |  | check
23.1.2 |  |  | Safety issues solved and documents completed | Safety Engineer |  | check
23.1.3 |  |  | Open issue list agreed | Customer |  | check
Number |  |  | Outputs | Output to | Link / Workinstruction | Output State (Open ¦ Done ¦ Work ¦N/A) | Comment
23.2.1 |  |  | FAC meeting minutes | Customer / Project Manager | Meeting Minutes | -
23.2.2 |  |  | FAC document signed | Customer / Project Manager | FAC Document_EN | - | FAC Document_DE
23.2.3 |  |  | Open issue list updated | Customer / Project Team |  | -
23.2.4 |  |  | Changes documented from the jobsite | Project Manager |  | -
23.2.5 |  |  | Jobsite closing report | Project Manager | Job Site - Closing Report | - | Job Site Closing Report
23.2.6 |  |  | Handover list for customer tooling | Customer | Job Site Toolbox handover list | -
| Place | Date | Jobsite Manager | Signature
4
16
5
17
18
20
21
22
23
19